## Sheet1
No | Description | Module | Tester Status | Developer Status | Date | Comments | Reference | stack | Developer commnet
1 | Send Billable and Status as required true from the backend. | Project > Add Task | Pending | Complete | 2025-04-28 | Backend | https://prnt.sc/ylX37FV9Uuvn | Changes are not showing. | job_status should be required = true.
this is done, actually this needs to done from database, so i have changeed the function,
2 | Send billable, boolean_default value as true from backend | Project > Add Task | Pending | Complete | 2025-04-28 | Backend | https://prnt.sc/39FVtDrPsn74 | Changes are not showing.
3 | Manage columns is working still showing server error. | Project > Resources | Tested | Complete | 2025-04-28 | Frontend | https://prnt.sc/sSIjfiDKbKZK |  | Meenaz: Wrong api is calling, check the user preference api
4 | Asbestos type configuration message is not coming . | Project > Add Task | Tested | Complete | 2025-04-28 | Frontend | https://prnt.sc/7IsatMOaTRdO |  | Use the api "Job asbestos-type"
5 | Hours_for_job values are not coming. | Manual Entry | Tested | Complete | 2025-04-28 | Backend | https://prnt.sc/nRatkIJRGEPj
6 | Remove shift premiums night% also correct the spelling of (SHIFT PREMIUM Afternoon). | Manual Entry | Pending | Complete | 2025-04-28 | Backend | https://prnt.sc/3_pqSACOn6P2 | Changes are not showing.
7 | Count summesion is worng is project has 2 1st level approvers. | Timesheet | Tested | Complete | 2025-04-28 | Backend | https://prnt.sc/LHpoKPBbMW_t
8 | Unable to add 1st level approver in the project settings. | Project > Settings | Tested | Complete | 2025-04-28 | Backend | https://prnt.sc/ifaPv7gWpUCG
9 | Entry is eddited and assinged to next day, still showing in the previous date. | Project > Timesheet | Tested | Complete | 2025-04-28 | Backend | https://prnt.sc/zcPjLBsEOTki
10 | entry is getting vanished after approving it from approve all entries button. (If 2nd level approver creating entries from bulk resource then it is not getting vanished.) | Project > Timesheet | Tested | Complete | 2025-04-28 | Frontend / Backend | https://prnt.sc/sRb6fyRJyEsf |  | Not reproducible, entry is succefully approved
11 | Month view button is not working | Project > Timesheet | Tested | Complete | 2025-04-28 | Frontend | https://prnt.sc/1PF6nVD2GHOc | Showing bad request error | Use the api from postman named: Monthly View
12 | In User entry, edit entry button is showing for 1st level and 2nd level approver.(Check user has access or not). | Project > Timesheet | Tested | Complete | 2025-04-28 | Frontend | https://prnt.sc/CkLgi2FK9PuW
13 | Export Timesheet button is not working. | Project > Timesheet | Pending | Pending | 2025-04-28 | Frontend / Backend | https://prnt.sc/fVFhzy5Hp-cf
14 | Loa entries (Only time is showing in the timesheet table) | Project > Timesheet | Tested | Complete | 2025-04-28 | Backend | https://prnt.sc/RURoiWwDTJBt
15 | Manage coloumn is not working | Project > LOA | Tested | Complete | 2025-04-28 | Frontend | https://prnt.sc/EVBJCulemPNK |  | Change the api
16 | Entry is assigned to 1st level approver yasin ,still showing to foysal (foysal is another 1st level approver and if I approved it from foysal then it is geting both level approved). | Project > Timesheet | Tested | Complete | 2025-04-28 | Frontend / Backend | https://prnt.sc/9QLg0sbs72-r |  | Check once the foysal's role
17 | Employee update is not working. | Workforce | Tested | Complete | 2025-04-29 | Frontend / Backend
18 | Entries are not splitting properly | Project > Timesheet | Pending | Pending | 2025-04-29 | Backend | https://prnt.sc/bB0tNDuIqOVS
19 | There should be a conflict error. | Project > Timesheet | Tested | Complete | 2025-04-29 | Backend | https://prnt.sc/TqPX_rG-w8Ev
20 | Approve all entries (Table bautton ) is not working , Entry getting vanished after approving it from that button. | Project > Timesheet | Tested | Complete | 2025-04-29 | Frontend | https://prnt.sc/XnmYQMqWvwhZ |  | Not reproducible
21 | Unable to add approvers in the organization approver tab. | Organization | Tested | Complete | 2025-04-29 | Frontend | https://prnt.sc/JIQFUiBsK6hI |  | Meenaz: Change the field name emp_jobtitle to emp_jobrole
22 | In SG&A time aproval tab, manager is foysal and he edtited the entry and changed the approver to safwan , still entry is showing in the foysal's pending table. | SG&A | Tested | Complete | 2025-04-29 | Frontend / Backend | https://prnt.sc/QHNkkL0crIbg | Arbaz : Foysal is just a normal employee , his role is manager. | Just check once foysal is IT admin or payroll user, because they can see the entries
23 | Approve all entries button is not working for genenal . | SG&A | Tested | Complete | 2025-04-29 | Frontend | https://prnt.sc/IDgcbGV_OhR_ |  | use the api "Approve General Entries"
24 | Country is not coming in employee step 1 form | Employee | Tested | Complete | 2025-04-29 | Frontend | https://prnt.sc/q2bxpXx_ESRv
24 | Action is column is empty, there should be edit and delete functionality. | Cost Center | Tested | Complete | 2025-04-30 | Frontend | https://prnt.sc/Iz4JelZjgx7U |  | Need to check from backend (If permission label is "Cost Center Delete" ).
25 | Export Data button is not working | WCB | Pending | Pending | 2025-04-30 | Backend | https://prnt.sc/VXk7o9MLRAOf
26 | Values are not coming in the columns. | Burden Rate | Tested | Complete | 2025-04-30 | Frontend | https://prnt.sc/2kqpcmhRvMKF
27 | Export Data button is not working Getting server error. | NOC | Pending | Pending | 2025-04-30 | Backend | https://prnt.sc/nfF2XlLxOe8u
28 | Export Data button is not working Getting server error. | LOA Configuration | Pending | Pending | 2025-04-30 | Backend | https://prnt.sc/1uSfHT4xVP8G
29 | Cost typye export data is not coming in parent and child format | Cost_Type | Pending | Complete | 2025-04-30 | Backend
30 | There should be a action column buttons. | Custom Project | Pending | Pending | 2025-04-30 |  | https://prnt.sc/ALylL3TM6TNI |  | Please check the feature, and let me know if there needs to change something
31 | LOA entries are not showing in my timesheet tab. | My Timesheet | Tested | Complete | 2025-05-02 | Backend | https://prnt.sc/IxaA3xGBRbOg
32 | Need to add column values. | My Timesheet | Tested | Complete | 2025-05-02 | Frontend | https://prnt.sc/-FA39z8wiTwZ
34 | Single approve and approve all entry button is not working for ER project timesheet. | ER > Timesheet | Tested | Complete | 2025-05-02 | Frontend / Backend | https://prnt.sc/J3DN-2CSl6B2 |  | Use api "Approve ER Entries"
36 | Unable to add task in the custom project (SQL App). | Project Templates > Custom Project | Pending | Complete | 2025-05-02 | Backend | https://prnt.sc/RI7sB86szs_c |  | The issue is with the data, which i fixed
40 | General approve all entries button is not working , Showing success message but entry is not getting approved. | Team's Time status | Tested | Complete | 2025-05-07 | Backend
41 | Add cost center functionality is not working. | Cost Center | Tested | Complete | 2025-05-09 | Frontend | https://prnt.sc/8xRHEDNYEWQz |  | Meenaz: Change the api for post "Dimension Reference - C"
42 | Cost center table header button is not showing. | Cost Center | Tested | Complete | 2025-05-09 | Backend | https://prnt.sc/S7eKl7KgiZWk |  | Need to check if label name is coming same name from backend "Cost Center Create"
43 | Showing commit error on saving the union code after adding subhead in it. | Union Code | Tested | Complete | 2025-05-09 | Backend | https://prnt.sc/wOIlYl42clxZ
44 | Remove break time from backend. | My Timesheet | Tested | Complete | 2025-05-12 | Backend | https://prnt.sc/OnKmW66dMUPK
45 | In general endit entry form, premium values are not coming. | SG&A | Pending | Pending | 2025-05-12 | Frontend / Backend | https://prnt.sc/xYEu5SFW12Vx
46 | There should be loa amount if the check box is checked. | My Timesheet | Tested | Complete | 2025-05-13 | Frontend | https://prnt.sc/mrueSD7aUcvx
47 | There should be a column value | Stand fleet | Pending | Pending | 2025-05-13 | Frontend / Backend | https://prnt.sc/LacrALMIaxWc |  | Arbaz : From backend send required as false or put it outside the data object,
48 | Corrective data is not showing in the service log table. | Fleet > service log | Tested | Complete | 2025-05-14 | Backend | https://prnt.sc/zM5VTw6z59KN
49 | Provience is missing in the fleet data object. | Standard Fleet | Tested | Complete | 2025-05-14 | Backend | https://prnt.sc/l077u_OdweBL
50 | Getting server error while creating a new manual er entry , with less data ,sometime its working and sometime its not working. | ER Manual Entry | Tested | Complete | 2025-05-15 | Backend | https://prnt.sc/OFD3v_L1oBaL
51 | Showing wrong count for the project entries, employee is assinged for only hour still showing the 5 hrs. | Project Entry Table | Pending | Complete | 2025-05-16 | Backend | https://prnt.sc/tpRs2btOYWiD
52 | Data is not coming from the backend for the team's time status > pending tab. | Team's Time status | Tested | Complete | 2025-05-16 | Frontend / Backend | https://prnt.sc/QBYIwkEeAW0v
53 | Getting server error of teams time status > aproved tab. | Team's Time status | Tested | Complete | 2025-05-16 | Backend | https://prnt.sc/S1Y8de9Xekvr
54 | ER entry is pending for only 1 hr , but it showing 4hrs.(draft + pending + approved) | Team's Time status | Tested | Complete | 2025-05-16 | Backend | https://prnt.sc/l-fO3v7wS4PA
55 | https://prnt.sc/NDWG_3SwJejS |  | Tested | Complete | 2025-05-17 | Frontend
56 | In my timesheet page, first call get-week api, after success call all the apis which required on that page |  | Tested | Complete | 2025-05-17 | Frontend
call clock in api only if when get-week api give the response clokin-enable true
57 | In Pending ER teams time status, If I approved form manager then entry is getting approve but time is getting double. (Before approved 4 hrs, After approved 8 hrs) | Team's Time status | Pending | Pending | 2025-05-19 | Backend | https://prnt.sc/OgEIXt8Hmg1w
58 | Download excel format and Export data is not working. | All Cost Center | Tested | Complete | 2025-05-19 | Backend | https://prnt.sc/sK_lwmIYC8wl
59 | There should be a union subhead tab , if union has subhead | Union Code | Tested | Complete | 2025-05-20 | Frontend | https://prnt.sc/YprkOJe31oZI
60 | Need to map values. | WCB | Pending | Pending | 2025-05-20 | Frontend / Backend | https://prnt.sc/mAkVQm6hB8Hq | Arbaz : Dimensions are not coming from backend. https://prnt.sc/oLVS7hwIL_vX
61 | Download excel format is not working. | Compensation | Pending | Pending | 2025-05-20 | Frontend | https://prnt.sc/yQeseQxItP6m | only compensation remove tax.
62 | Employee name is not coming in the header. | Employee | Tested | Complete | 2025-05-20 | Frontend | https://prnt.sc/u1eY-P5qgtVo
63 | Some employee table values are not coming to fix it from backend and frontend. | Employee | Pending | Pending | 2025-05-20
64 | If I created project using bulk upload, then dimensions are coming empty in the project edit tab. | Project | Pending | Pending | 2025-05-20 | Backend | https://prnt.sc/C8XE60L-CC7i
65 | Project archive is not working. | Project | Tested | Complete | 2025-05-20 | Frontend / Backend | https://prnt.sc/ZrBFvkg4vnnA
66 | There hsould be a conflict error in the bid and development entries | Bid and dev. Time entrues | Pending | Pending | 2025-06-12 | Backend | https://prnt.sc/UZ0qaAbsHoXI
|  |  | Pending | Pending | 2025-06-12
67 | Unable to add union code in the employee personal details form, If I am selecting union code as yes then form is not getting submited. | Employe > Employement Details | Pending | Pending | 2025-06-23 | Backend | https://prnt.sc/5Aa_IOiKSpbo
68 | Showing server error while saving the employee work details, If I am selecting union code for employee while selecting the employement details form then only it is showing server error. | Employee > Work Details | Pending | Pending | 2025-06-23 | Backend | https://prnt.sc/pGtUFrOPJEbW
69 | There should be a proper status details in the status trail. | Employee > Status | Pending | Complete | 2025-06-23 | FrontEnd | https://prnt.sc/eKzwpGWcAjY2
70 | Send OnBoarding Email button is missing on the page. | Employee > Status | Pending | Complete | 2025-06-23 | FrontEnd | https://prnt.sc/vv7ShgjUXLvl
71 | Organization name is not showing in the employee table, Need to send full organization object from backend. | Employee | Pending | Pending | 2025-06-23 | Frontend / Backend | https://prnt.sc/-HsPmm9F0rx5
72 | Employee Froce logout functionality is not working. | Employee | Pending | Pending | 2025-06-23 | Frontend / Backend | https://prnt.sc/lnvsE7C1XEje | In test server it is working.
73 | Employee Delete functionality is not working | Employee | Pending | Pending | 2025-06-23 | Frontend / Backend | https://prnt.sc/uNPsJJT27LhR
74 | If only personal information is filled and i am directly going to the work details tab , then 404 error is coming. | Employee | Pending | Complete | 2025-06-24 | Frontend | https://prnt.sc/_FN0AKJ1pwCA
75 | If we have only one work details form then delete button should be hidden. | Employee > Work Details | Pending | Complete | 2025-06-25 | Frontend | https://prnt.sc/-uK48BJwXPnI
76 | I have added the approver in the organization approver tab, but whenever I am creating a new project those approvers are not coming in the settings approver tables. | Project > Settings | Pending | Pending | 2025-06-25 | Backend | https://prnt.sc/5XsDdk_DSxb-
77 | Newly added employees are not coming in the add resource tab, I think this is their burden rate issue. | Project and Organization | Pending | Complete | 2025-06-25 | Backend
78 | If I am deleting the general entries then entries is getting deleted also it is showing 0 hrs but whenenver i am creating a new entry on that time it is showing the conflict error. | General | Pending | Pending | 2025-06-25 | Backend
79 | Masking configuration searc his showing duplicate values. | Masking Configuration | Pending | Pending | 2025-06-25
80 | Delete single ER row is not working for 1st and 2nd level approver | ER > Pending | Tested | Complete | 2025-07-09 | Backend | https://prnt.sc/rTlt5covgvGZ
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-07-09
|  |  | Pending | Pending | 2025-06-25

## Sheet2
No | Description | Module | Tester Status | Developer Status | Date | Comments | Reference | stack | Developer commnet
1 | After Deleting Tooltip,still showing in particular Field | Admin > Tooltip | Pending | Pending | 2025-09-26 |  | https://prnt.sc/TQBn41YTzY84
2 | Added Sucessfully but not working | Admin > Masking | Pending | Pending | 2025-09-26 |  | https://prnt.sc/Iw7aSuLQcH6q
3 | If I Manually Type in Provience instead of dropdown ,form accepted it. | Admin > Organisation > add button | Pending | Pending | 2025-09-26 |  | https://prnt.sc/V-_1iaPctkU0
4 | if I Manually Type in Unit instead of dropdown ,form accepted it. | Workforce >work Configuration >Union Code >Has Subhead | Pending | Pending | 2025-09-26 |  | https://prnt.sc/H_rZ6qDocoS3
5 | When I check the 'Has Subhead' checkbox, values are displayed with the 'Save Changes' button. When I uncheck it, the values are reset. However, after reloading the page, the values are displayed again. | workforce >work Configuration >Union Code >Has Subhead | Pending | Pending | 2025-09-26 |  | https://prnt.sc/gm4sA_KfFVAc
6 | If I Manually Type in Provience instead of dropdown ,form accepted it. | Workforce >work Configuration >Union Code >WCB | Pending | Pending | 2025-09-26 |  | https://prnt.sc/KHk3DDboivHR
7 | If I Manually Type in Provience instead of dropdown ,form accepted it. | Workforce >work Configuration >Union Code >compensation | Pending | Pending | 2025-09-26 |  | https://prnt.sc/0BEivxFdRva4
8 | When I deselect all columns in 'Manage Columns', all columns disappear | Workforce >work Configuration >Payroll Setting >Pay Calender | Pending | Pending | 2025-09-26 |  | https://prnt.sc/CZJNP8RmwrUA
9 | Want full desription on PAY CALENDER | Workforce >work Configuration >Payroll Setting >Pay Calender | Pending | Pending | 2025-09-26
10 | If I Manually Type in Provience instead of dropdown ,form accepted it | Admin>Organisation>Office Adresses | Pending | Pending | 2025-09-26 |  | https://prnt.sc/6-7dZrmHpbzI
11 | Almost All Proviences accept string or integer instead of dropdown |  | Pending | Pending | 2025-09-26
12 | Search field is not working As per expectation ,vice name data present In Table but whenever I search intead of vice other data displayed | Workforce >work management > job title | Pending | Pending | 2025-09-29 |  | https://prnt.sc/B_KtcOqTrJTq
13 | When I deselect all columns in 'Manage Columns', all columns disappear | Workforce >work management > job role | Pending | Pending | 2025-09-30 |  | https://prnt.sc/-OxnJVi_lAeQ
14 | Action Field Present at first column intead of last | Workforce >work management > job role | Pending | Pending | 2025-10-01 |  | https://prnt.sc/hmMbSqN9JV2n
15 | If I Manually Type in Provience instead of dropdown ,form accepted it | WorkForce>Timesheet >Calendar>Province wise holiday | Pending | Pending | 2025-10-01 |  | https://prnt.sc/dRyPDXpDGEUn
16 | when I click download excel file ,error displayed | WorkForce>Timesheet >BD Task | Pending | Pending | 2025-10-01 |  | https://prnt.sc/r8S6HSZxR0j6
17 | Creating a Employee and Fill the All Forms but whenever I delete Work Details user getting vanished from active and draft table but present in database | Workforce >Work Management >Employee | Pending | Pending | 2025-10-10 |  | https://prnt.sc/CssRDQhr3qDr,
18 | When I deselect all columns in 'Manage Columns', all columns disappear | Workforce >Work Management >Employee | Pending | Pending | 2025-10-16 |  | https://prnt.sc/rYw8xDdBHvYD
19 | Add Same Data At a Time and this field is Optional but it holds both data at same time | Projects > Project Templetes >Standard Project> Update > Setting | Pending | Pending | 2025-10-16 |  | https://prnt.sc/tjkwDFKSsxDh
20 | Accept Duplicate Data in Task List | Projects > Project Templetes >Standard Project> Update > Task | Pending | Pending | 2025-10-17 |  | https://prnt.sc/DWezpi5fK3lk
21 | Add Same User Multiple Time In First, Second And Leadership Table | Projects > Project Templetes >Standard Project> Update > Setting | Pending | Pending | 2025-10-17 |  | https://prnt.sc/6hKmmizYVFiK
22 | Whenever Export Data of "Name".In Table 281 entries are available but in excel 2174 data shows | Project > Project Templets> Standard Project >Export Data > Name | Pending | Pending | 2025-10-19 |  | Excel : https://prnt.sc/UXlkMk92b8k1,https://prnt.sc/7th2QuvYpOqr
23 | In the Mention dropdown field, manually typing any string will be accepted and saved successfully. After saving, the field will be cleared. However, these fields are mandatory. | Project > Project Templets> Standard Project >Add Job Data | Pending | Pending | 2025-10-20 |  | https://prnt.sc/d7iifdQeFvQF
24 | Duplicate data accepted, but when I remove a single column, both entries are removed at the same time. After refreshing, the old data reappears in the table. | Project > Project Templets> Standard Project >Setting | Pending | Pending | 2025-10-21 |  | https://prnt.sc/JK5DvCbo5Jri
25 | After deleting some tasks from the task list, they still appear in the subjob when trying to allocate an employee resource. | Project > Project Templets> Standard Project >Task | Pending | Pending | 2025-10-22 |  | https://prnt.sc/RGgty7pMrjcg
26 | Not Working, Always Show Error , Sometimes Code: 500 Message: Server Error OR [OBJECT,OBJECT] | MyTimesheet > Entries > View Details >Edit | Pending | Pending | 2025-11-04 |  | https://prnt.sc/ZUoFMaa6B3L5
27 | In LOA entries Whenever trying to edit not edited properly | MyTimesheet | Pending | Pending | 2025-11-04 |  | https://prnt.sc/_7BrSPQT1RgE
28 | In LOA entries Whenever trying to edit from View Details ,not edited properly | MyTimesheet | Pending | Pending | 2025-11-04 |  | https://prnt.sc/hg3v7H0owWHe
29 | Whenever an LOA entry is created for an employee, it automatically appears in the first,second -level approval without sent from the employee’s end. | MyTimesheet >Loa Entries | Pending | Pending | 2025-11-04 |  | https://prnt.sc/29d9QzvmhcZj
30 | No Any Entry In Table But Still Count is 1 | MyTimesheet >Loa Entries | Pending | Pending | 2025-11-04 |  | https://prnt.sc/ABlT3_C5T3OT
31 | LOA entry is also Showing To both Approvals without sending From Users End | MyTimesheet >Loa Entries | Pending | Pending | 2025-11-04 |  | https://prnt.sc/eS9J73L5rRK4
32 |  |  | Pending | Pending | 2025-11-10
33 |  |  | Pending | Pending | 2025-11-11
34 |  |  | Pending | Pending | 2025-11-12
35 |  |  | Pending | Pending | 2025-11-13
36 |  |  | Pending | Pending | 2025-11-14
37 |  |  | Pending | Pending | 2025-11-15
38 |  |  | Pending | Pending | 2025-11-16
39 |  |  | Pending | Pending | 2025-11-17
40 |  |  | Pending | Pending | 2025-11-18
41 |  |  | Pending | Pending
42 |  |  | Pending | Pending
43 |  |  | Pending | Pending
44 |  |  | Pending | Pending
45 |  |  | Pending | Pending
46 |  |  | Pending | Pending
47 |  |  | Pending | Pending
48 |  |  | Pending | Pending
49 |  |  | Pending | Pending
50 |  |  | Pending | Pending
51 |  |  | Pending | Pending
52 |  |  | Pending | Pending
53 |  |  | Pending | Pending
54 |  |  | Pending | Pending
55 |  |  | Pending | Pending
56 |  |  | Pending | Pending
57 |  |  | Pending | Pending
58 |  |  | Pending | Pending
59 |  |  | Pending | Pending
60 |  |  | Pending | Pending
61 |  |  | Pending | Pending
62 |  |  | Pending | Pending
63